## P n G
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
ITEM | PAYMENT | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
NO |  | SECTION A: PRELIMINARY AND GENERAL |  |  |  | R
Note: Contractor's Rates to consider: Contractor to Hire at least 6 LOCAL personnel/labourers at not less than R27.58/hour labour rate for a 4 months Contract Period with Actual Works
1 | SABS 1200 A | SECTION 1: PRELIMINARY AND GENERAL
1.1 |  | SCHEDULED FIXED-CHARGE AND VALUE-RELATED ITEMS
1.1.1 |  | Fixed Preliminary, Value Related and General Charges: Facilities required by Contractor: Site office (16m2), storage, tools, equipment, water supplies, electric power, communication, dealing with water, access and Ablution facilities on site et | Sum | 1
SCHEDULED TIME RELATED
1.2.1 |  | Time Related Preliminary and General Charges: Facilities required by Contractor: Site office (16m2), storage, tools, equipment, water supplies, electric power, communication, dealing with water, access and Ablution facilities on site et | months | 4
1.2.2 |  | Health and Safety obligations | months | 4
1.3 |  | SUMS STATED PROVISIONALLY BY THE ENGINEER
1.3.1 |  | Check Tests by an Independent Laboratory | Prov Sum | 1 | 15000 | 15000
1.3.2 |  | Overheads, charges and profit on item above | % | 15000
1.3.3 |  | Sign boards | No | 2
1.3.4 |  | Provision for employment of a Community Liaison Officer (4months) | Prov Sum | 1 | 26000 | 26000
1.3.5 |  | Overheads, charges and profit on item above | % | 26000
1.4 |  | Ocupational health and safety
1.4.1 | PS10 | Without limiting the generality of the provisions of clause 4.3.1 of the GCC second edition 2010, the contractor's attention is drawn to the provisions of the following regulations: "Construction Regulations, 2014 issued in" terms of the Occupational Health and Safety Act (Act No 85 of 1993) as amended. The employer reserves the right to take responsible action should any breaches of the above regulations and / or the Employer's Requirements come to their notice, including the provision of and insistence on the use of hard hats, overalls, ear protection plugs, eye protection goggles, reflective safety vests, gloves, safety boots, belted safety harnesses, barrications of works, Inductions, Fitness tests, respiratory gear and screening, Covid etc. by any person on the site, the cost for purchase of which will be borne by the contractor | Sum | 1
TOTAL SECTION A CARRIED TO SUMMARY

## EARTHWORK
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
ITEM | PAYMENT | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
NO |  | SECTION B: EARTHWORKS |  |  |  | R
2 | SABS 1200D | EARTHWORKS
2.1 |  | Site Preparation
2.1.1 |  | clear and grub | m² | 600
2.1.2 |  | Excavate in all material for the top 200mm platform and dispose | m³ | 100
2.2 |  | Restricted Excavation
2.2.1 |  | Excavate in all material for foundations and footings and use for backfill or dispose | m³ | 40
2.2.2 |  | Intermediate Excavation | m³ | 3
2.2.3 |  | Hard Rock Excavation | m³ | 3
2.2.4 |  | Excavation and laying, including bedding and backfilling - up to 1,2m depth on soft to intermediate soil material for Pipeline upto 110mm | m | 200
2.3 |  | Selected Layers
2.3.1 |  | import G5 and Backfill to foundations and walls with material from borrow pit on site and placed in 150mm layers and compacted to 95% Mod AASHTO under concrete floor and bases. | m³ | 250
2.4.2 |  | Termite treatment or soil poisoning by safe and effective specialist with Chlordane or Aldrin type termite soil insecticide all in accordance with SABS 0124-1977: Under solid floors including forming furrows against foundation walls, etc. and filling in furrows | m² | 500
TOTAL SECTION B CARRIED TO SUMMARY

## BRICK AND CONCRETE 1
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION C: CONCRETE, BRICKWORK AND FINISHES |  |  |  | R
SECTION C: LAYER HOUSE
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no LDALH001, LDALH002, LDALH003, LDALH004, MPS 103
3.1 | SABS 1200 G | CONCRETE (STRUCTURAL)
3.1.1 |  | Formwork
3.1.2 |  | Rough vertical plane to walls, footings and slabs below ground | m² | 0.5
3.1.3 |  | Smooth vertical plane to walls and slabs above ground and inside chambers | m² | 24
3.2 |  | Reinforcement
3.2.1 |  | Weld mesh Ref. 193 to Poultry house and ablution floor | m² | 400
3.2.2 |  | Weld mesh Ref. 617 to Poultry house concrete base | m² | 14.4
3.2.3 |  | Weld mesh brickforce on every third row and every row on foundation and above lintol in the following width, 220 mm and 2.8mm thickness | m | 2300
3.2.4 |  | Weld mesh brickforce on every third row and every row on above lintol in the following width, 110 mm and 2.8mm thickness | m | 200
3.3 |  | Concrete
3.3.1 |  | Grade 20MPa/19mm, 100mm thickness apron | m³ | 10
3.3.2 |  | Grade 25MPa/19mm structural concrete to floors | m³ | 65
3.4 |  | Unformed Surfaces
3.4.1 |  | Power float finish to floors | m² | 300
3.4.2 |  | Wood float finish to apron slabs and Ramp | m² | 135
SUB TOTAL SECTION C CARRIED FORWARD

## Brick and concrete 2
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION C: CONCRETE, BRICKWORK AND FINISHES |  |  |  | R
Brought forward
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no VLH01, ,VLH1, VLH2, VLH3, VLH4,VLH5
3.5 |  | BRICKWORK
All bricks to be SANS approved. Price to include supply, transport to site including all mortar, pointing, scaffolding and support.
Walling with clay stock bricks on the inside (NFP type) and clay bricks on the outside (FBS type) for the layer house, packshed and ablution foundations all to SANS 227
3.5.1 |  | a) 230 mm wide brick wall | m² | 120
3.5.2 |  | b) 115 mm wide brick wall | m² | 90
Walling with Nasbraska or similar approved Facebrick point finished on the outside and on the inside
3.5.3 |  | a) 230 mm wide brick wall | m² | 130
3.5.4 |  | b) 115 mm wide brick wall | m² | 20
3.6 |  | AIR BRICK
3.6.1 |  | Concrete air brick | no | 6
3.7 |  | WATERPROOFING
3.7.1 |  | a) One layer of 375 micron "Consol Plastics" Brickgrip DPC" embossed damp proof course in 230mm walls | m | 100
3.7.2 |  | b) One layer of 250 micron "Consol Plastics Gunplas USB Green" waterproof sheeting sealed at laps with "Gunplas Pressure Sensitive Tape" under surface beds. | m² | 335
3.8 |  | PRE-CAST LINTELS 70 x 110
On internal skin above external doors and windows
3.8.1 |  | Lintels 0.9 m | no | 4
3.8.2 |  | Lintels 1.2 m | no | 2
3.8.3 |  | Lintels 1.8 m | no | 3
3.8.4 |  | Lintels 2.4 m | no | 2
3.9 |  | DOORS AND WINDOWS
Doors
3.9.1 |  | Supply & install meranti wooden door & with steel frame, complete with chromium plated handles & 3 lever lock, door catch and painted to specification:
3.9.1.1 |  | a) 915x2035 mm | No | 4
3.9.2 |  | Supply & install hard wood door & with steel frame, complete with chromium plated handles & 3 lever lock, door catch and painted to specification:
3.9.2.1 |  | a) 915x2035 mm | No | 2
SUB TOTAL SECTION C CARRIED FORWARD

## brick and concrete 3
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION C: CONCRETE, BRICKWORK AND FINISHES |  |  |  | R
Brought forward
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no VLH01, ,VLH1, VLH2, VLH3, VLH4,VLH5
3.9.3 |  | Supply & install steel door & with frame, complete with chromium plated handles & 3 lever lock, door catch and painted to specification:
3.9.3.1 |  | a) 813 x 2032mm | No | 2
3.9.3.2 |  | b) 1613 x 2032mm | No | 1
3.9.4 |  | Manufacture, Supply and Install Burglar doors for all extenal doors and painted with two coat of etch primer and two coat of black enamel paint
3.9.4.1 |  | a) 813 x 2032mm | No | 2
3.9.4.2 |  | b) 1613 x 2032mm | No | 1
3.1 |  | STEEL WINDOW FRAMES
Supply and install steel window frame with 4mm glazing and burglar proofed
3.10.1 |  | NE 1 window frames, size 533 x 654mm | No | 4
3.10.2 |  | NE 2 window frames, size 1022 x 654mm | No | 2
3.10.3 |  | NE 4 window frames, size 1511 x 654mm | No | 2
3.10.4 |  | D22 window frames, size 2000 x 1245mm | No | 2
3.10.5 |  | Aluminium horizontal sliding window with glazing, 1800 x 1200 mm | No | 1
3.11 |  | Solid flush panel door with 3mm commercial ply wood finish for painting to both sides and hardwood concealed edges, hung to steel frames (elsewhere)
3.11.1 |  | 40mm Door 813 x 2032mm high | No | 6
3.12 | PD023 | PLASTERING
3.12.1 |  | 15 mm Cement Plaster on Brickwork | m² | 65
3.13 | PD09 | PAINTWORK
On Plaster
3.13.1 |  | One coat Plaster Primer thinned with 10% turpentine and two coats of Super Acrylic PVA | m² | 65
TOTAL SECTION C CARRIED TO SUMMARY

## FABRICATED STEEL STRUCTURE (2
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION D: FABRICATED STEEL STRUCTURE AND ROOFING |  |  |  | R
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no LDALH001, LDALH002, LDALH003, LDALH004, MPS 103
4.1 | SANS 1200H, HA, 121 | STRUCTURAL STEEL
4.1.1 | PD10 | Manufacture, supply, fabricate, surface preparation, shop priming, delivery to site & erect and fix the following, including all drilling, welding, bolts, nuts, frame members, cleats, brackets, gussets, packs, nuts, bolts, washers, roof screws, roof washers, etc. as per provided drawings. Use IPE 160, 25m x 11m | Sum | 1
4.1.2 |  | Painting on site of steel structure after erection with one coat universal undercoat and two coats gloss enamel applied on site after erection, including for touch-up work and preparation required before painting. | Sum | 1
4.2 |  | ROOF SHEETING super structure
4.2.1 | PD10.3 | Supply and fix including all fixing screws, IBR 0.55mm thick Chromadek traffic green coated on the Roof to sandwich the insulation for roof, etc. for a 25x11m building as per provided drawing. | m² | 255
4.3 |  | INSULATION
4.3.1 |  | Supply and install Alububle or similar approved roof expanded Polystyrene insulation , rate must include all straining wires, etc. spaced according to the manufacturers specifications etc. | m² | 255
4.4 |  | ABLUTION ROOFING
Supply and install roof structure (drawing MPS103)
4.4.1 |  | 0,5mm Full-hardened G275 spelter galvanised IBR sheet, 500 mm overhang | m² | 105
4.4.2 |  | Beams, 100x50x3 mm rectangular hollow sections, 5m long | No | 12
4.4.3 |  | Purlin, 76x338x3 mm rectangular hollow sections, (6@ 6.8 m long) | m | 120
4.4.4 |  | Flat straps connecting beams to the wall, 50 x 3 mm plate, 800mm long | No | 30
4.4.5 |  | M12x 250 bolt, nut and 2 washers connecting flat straps to the wall | No | 3
4.4.6 |  | Screws, cleats and bolts for fastening of roof sheeting to structure | No | 3
SUB TOTAL SECTION D CARRIED FORWARD

## FABRICATED STEEL STRUCTURE AND
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION D: FABRICATED STEEL STRUCTURE AND ROOFING |  |  |  | R
Brought forward
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no LDALH001, LDALH002, LDALH003, LDALH004, MPS 103
4.5 |  | CEILINGs
6.8mm gypsum ceiling with Bishop strip joints. fixed to 38 x 38 SA pine brandering at max 400mm centres\ and supported 114mmx 38mm beam
4.5.1 |  | 6.8mm gypsum ceiling
4.5.1.1 |  | a) Packging and store room | m² | 12
4.5.1.2 |  | b) Ablution | m² | 26
4.5.1.3 |  | SA Pine beam (114mm x 38mm) | m | 36
4.5.1.4 |  | SA Pine brandering (38mm x 38mm) | m | 90
4.5.1.5 |  | Bishop strip joints. | m | 50
4.5.1.6 |  | Galvanised Steel Clout Nails (32 x 3mm) | kg | 2
4.5.1.7 |  | Round Wire Nails 100mm x 3.55mm | kg | 1
4.5.1.8 |  | Nail Concrete Fluted 100mm | kg | 1
4.6 |  | EXPANDED MESH AND CURTAIN RAILS
4.6.1 | PD11.7 | Suppy & install expanded mesh on the sides of the poultry house structures (60 m x 3 m high). Mesh should be strengthern by Square tube 65x65x2mm (25 x 25 x 2.0mm weldmesh wire in 25 x 25 x 2 square tubing frames, bolted to structure and painted with two layers of etch primer and two layers of black enamel paint) rate should include heavy duty hinge etc. | Sum | 1
4.6.2 | PD11.8 | Suppy & install curtain - 500kg/m² CANVAS (0.6m x 17.5m at the top and 3 m x 60m at the bottom for weather proof) on the sides of the poultry house structures with a winch and cable system. Supply and install separation curtain(PVC - SAIL TARPAULIN) | Sum | 1
4.7 |  | SAFE EQUIPMENT
4.7.1 |  | Supply, Deliver and Install Fire Extinguisher, 9 kg, SABS 1910 Approved | No | 1
4.8 |  | RAINWATER DISPOSAL
4.8.1 |  | 0,6mm thick galvanised sheet iron of G275 spelter in:
4.8.2 |  | 76x100mm rectangular eaves gutter | m | 54
4.8.3 |  | Stopped end to fit item (a) | no | 6
4.8.4 |  | Mitred angle to fit item (a) | no | 6
4.8.5 |  | 76x100mm rectangular rainwater pipes | m | 12
4.8.6 |  | Crimped shoe | no | 6
4.8.7 |  | Eaves offset | no | 6
4.8.8 |  | 76x100mm rectangular rainwater spout 300mm long | no | 6
TOTAL SECTION D CARRIED TO SUMMARY

## WATER AND SEWAGE (3)
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION E: WATER, SEWAGE AND ELECTRICAL WORKS |  |  |  | R
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no LDALH001, LDALH002, LDALH003, LDALH004, MPS 103
5.1 |  | INSTALLATIONS
5.1.1 |  | Equal and approved or 525 x 420mm "Sola" white vitreous china wash hand basin with two tap holes on wall bracket plugged to wall, "Cobra Aquila 404" basin set comprising one pair of pillar taps and one waste, plug and chain, two "Cobra 1060" fullway ballcocks and 32 x 40mm chromium plated bottle trap complete | no | 2
5.1.2 |  | Equal and approved or Hibiscus close coupled WC suite "code 772602" comprising wash down closet pan with straight outlet P-trap, 9 litre cistern complete "code 710531" with flush pipe and double flap painted timber seat, one 15mm "Cobra 1060-15" full way ball cock and 110mm PVC pan connector complete | no | 2
5.1.3 |  | Straight Pan Connectors | No | 2
5.1.4 |  | Standard white glazed toilet roll holder | No | 2
5.1.2 |  | Stainless steel grab rail 45 deg. Angle (Oblique grab rail with two flanges 400 x 400 x 35) | No | 2
5.1.6 |  | 50mm uPVC pipes connecting sanitary fittings to main sewer line | m | 12
5.1.7 |  | All 50mm inspection eyes, bends and junctions required to complete connection | No | 4
5.1.8 |  | 110mm uPVC pipes laid to form main sewer line | m | 24
5.1.9 |  | 110mm inspection eyes, roding eyes, bends 90 degrees, junctions and fittings required to complete sewer connection from main line to sewer tank | No | 3
5.1.10 |  | 110mm diameter vent horn inspection eye including all necessary fittings | No | 2
5.1.11 |  | 15mm connector braided | No | 4
5.1.12 |  | 15mm conmression CXC ISO valve W-mach | No | 4
SUB TOTAL SECTION E CARRIED FORWARD

## WATER AND SEWAGE (2)
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION E: WATER, SEWAGE AND ELECTRICAL WORKS |  |  |  | R
Brought forward
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no LDALH001, LDALH002, LDALH003, LDALH004, MPS 103
5.1.13 |  | 20 mm brass gate balve | No | 5
5.1.14 |  | 22 -15mm compression CXC straight coupler | No | 5
5.1.15 |  | 22 mm compression CXC straight coupler | No | 4
5.1.16 |  | 20mm copper pipe | m | 12
5.1.17 |  | 15mm copper pipe | m | 12
5.1.18 |  | 20mm Polycop pipe, red | m | 100
5.1.19 |  | 15mm Ball-o-stop | No | 1
5.1.20 |  | 32 mm 303CP basin waste union and 309CP anti theft plug with spindle | No | 2
5.1.21 |  | 15mm 3293ST "Stella" mixer or similar approved | No | 1
5.1.22 |  | 15mm 232/350CP angle regulating valve and | No | 1
5.1.23 |  | Shower rose with 5 setting | No | 2
5.1.24 |  | 50mm shower trap with 110mm x 110mm grid crome | No | 2
5.1.25 |  | Soap baskey crome | No | 2
5.1.26 |  | 450x600x6mm "GG" quality polished glass mirror above wash basin: Fix to wall postion as on site with round nose chromium plated mirror screws (4 per mirror and 1 per basin) | No | 2
5.1.27 |  | 600x19mm stainless steel chromium plated towel rail: complete with chromium plated end brackets plugged and screwed to wall | No | 2
5.1.28 |  | shower railings and curtains, seating bench, clothes hooks and soap holders in each shower area | no | 2
SUB TOTAL SECTION E CARRIED FORWARD

## WATER AND SEWAGE
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION E: WATER, SEWAGE AND ELECTRICAL WORKS |  |  |  | R
Brought forward
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no LDALH001, LDALH002, LDALH003, LDALH004, MPS 103
5.2 |  | SOLAR GEYSER
5.2.1 |  | indirect pump circulation split solar water heating system with one 2500 x 1000 x 80mm high flat solar panel collector (code: SOL-PANEL-2.5) mounted onto an adjustable frame, system to include 150 Litre SOL-200-IND round solar water heater complying with SANS 1307:2007, overall size 594mm diameter x 1360mm long with 22mm copper pipe and operating at 400kPa with 400kPa Multi pressure control and expansion relief valve (Code: KHN3.214), 100KPa expansion relief valve, 20mm draincock and 22mm insulated pipe work including two vacuum breakers (Code: KHN4.200CX) installed on hot and cold water supply, including all necessary brackets, Glycol, lagging, thermostatic mixing valve, 12V circulating pump, 12V PV panel and polyethylene drip tray. including all other necessary fittings & fixtures | Sum | 1
5.3 |  | SEPTIC TANK
Supply and install
5.3.1 |  | 1700 diam. x 1600 high 3000 litre polyethylene septic tank, rate to include excavation, backfill, connection and all necessary fittings. | Sum | 1
5.3.2 |  | Construct a soakaway (french drain) overall size 5000 x1000 x1200mm deep wide french drain rates to include excavation, Geomembrane, 50-80mm crush stone, backfill etc. as per the drawing LDA/ABD001 | Sum | 1
5.3.3 |  | Bidum A4 Geotextile Membrane, 4.8 x 5m long | m² | 24
E4 |  | WALL TILING
5.4.1 |  | 152 x 152 x 5mm White glazed ceramic tiles fixed with adhesive to plaster (plaster elsewhere) price must include 2mm spacers, bonding liquids atc | m² | 10
5.4.2 |  | 300 x 300mm Ceramic tiles (Cost price R150/m²) fixed with adhesive to power floated concrete and flush pointed with tinted waterproof jointing compound, price must include 2mm spacers, bonding liquids atc | m² | 30
TOTAL SECTION F CARRIED TO SUMMARY

## EQUIPMENT and ELECTRICAL
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
ITEM | PAYMENT | DESCRIPTION | UNIT | QUANTITY | RATE | AMOUNT
|  | SECTION G: EQUIPMENT, INSTALLATIONS AND ELECTRICAL WORKS |  |  |  | R
Carry out the following operation as applicable: Manufacture, supply, deliver, install, commission, test and attend to defects for the following items:
must be read in conjuction with drawing no LDALH001, LDALH002, LDALH003, LDALH004, MPS 103
6.1 |  | EQUIPMENTS
6.1.1 |  | 3 tier 2.4m layer cage modules @ 5 hens per cage and capacity of 150 hens complete with feeding trough, header tanks and nipple drinker lines etc. | No | 20
|  | Supply, install and commission electric powered magnetic balance method egg grader. Maximum capacity of 3 000 eggs per hour. Egg grading capacity between 34g and 100g. | No | 1
|  | Supply galvanised egg collection trolley. | No | 5
|  | Supply 300 x 300 mm plastic egg colletion trays. | No | 50
|  | Manufacture, Supply and install a complete manure removal system for 3 tier which include 1.5 kW Motor, galvanised scrapper, corner wheels, rope, screws etc. | No | 3
6.2 |  | BIRD WIRE NETTING NETTING AND CURTAIN
SAFE EQUIPMENT
6.2.1 |  | Supply, Deliver and Install Fire Extinguisher, 9 kg, SABS 1910 Approved | No | 1
6.3. |  | ELECTRICAL
Carry out the following operation as applicable: Manufacture, supply, deliver, install, wiring, fittings, distribution board, earthing systems, test, commision, provide COC and attend to defects for
6.3.1 |  | Solar panels, approximately 2172mm long , 1303 mm wide and 35 mm thickness, 600wh | No | 6
6.3.2 |  | Solar system 8KVA hybrid invertor | No | 1
6.3.3 |  | Batteries lithium ion output 10 Kwh, with accessories such as parallel cables (negative and positive), Communication parallel cable, Communication cable-to inverter, Ground wire, screws M6 etc. and 5 years warranty | Sum | 1
6.3.4 |  | Battery box: Battery Steel Cabinet with door -Fits 10 kw Output Batteries on above item with lockable mechanism, Environmental Control and earth swicth | Sum | 1
6.3.5 |  | Cabling, Wiring, DB, and Control Switches or Circuit breakers for the 8kVA system, linked to Eskom DB within the storage shed | sum | 1
6.3.6 |  | 8mm2 4 core armoured cable for wiring | m | 20
6.3.7 |  | Complete Portable Solar Charged Light System, with All 3 LED globes with individual on/off switch, All 3 LED globes with 3m length cable, 9V 3.5W solar panel and Battery unit shold be able to be recharged by 220V AC electricity | No | 4
6.3.8 |  | Cabling, Wiring, DB, and Control Switches or Circuit breakers for the 6kVA system | Sum | 1
6.3.9 |  | LED Solar Floodlight & Panel 100w (cable 3m) | No | 4
6.3.10 |  | Ceiling Solar Floodlight & Panel 300w (cable 5m) | No | 10
6.4 |  | COMMISSIONING
6.4.1 |  | Commissioning of all works: water and electrical | Sum | 1
TOTAL SECTION E CARRIED TO SUMMARY

## SUMMARY
LIMPOPO DEPARTMENT OF AGRICULTURE
CASP PROJECTS
3000 BIRDS LAYER PROJECT IN VHEMBE DISTRICT
SUMMARY
Section | DESCRIPTIONS OF WORKS | AMOUNT
No
A | PRELIMINARY & GENERAL
B | EARTHWORKS
C | BRICK AND CONCRETE
D | FABRICATED STEEL AND ROOF
E | WATER, SEWAGE AND ELECTRICAL WORKS
G | EQUIPMENT, INSTALLATIONS AND ELECTRICAL WORKS
SUB-TOTAL A
10% CONTINGENCIES
SUB-TOTAL B
15% VAT
GRAND TOTAL CARRIED TO FORM OF OFFER & ACCEPTANCE