## Immerpan Summary
EQUIPPING AND WATER RETICULATION AT IMMERPAN PHASE 2 FOR LIVESTOCK AT SIX INDIVIDUAL IMMERPAN FARMS IN THE MOOKGOPHONG MUNICIPALILTY, WATERBERG DISTRICT IN LIMPOPO PROVINCE
SUMMARY OF SECTIONS
TOTAL SECTION A : PRELIMINARY AND GENERAL
TOTAL SECTION B : BELLEVUE
TOTAL SECTION C : HANGLIP
TOTAL SECTION D : DOORNPOORT
TOTAL SECTION E: VUURSTENLAGTE
TOTAL SECTION F: VANHEINING
TOTAL SECTION G: APPELFONTEIN
SUB TOTAL SECTION A-G
PLUS 10% CONTINGENCIES
SUB TOTAL
ADD 15% VAT
GRAND TOTAL, CARRIED TO FORM OF TENDER

## PG
No. | CLAUSE | SECTION A: PRELIMINARY & GENERAL | UNIT | QTY | RATE | AMOUNT
SANS 1200 A
A.1 | 8.3.1 | FIXED CHARGE AND VALUE-RELATED ITEMS (Max 5% SECTION B-E)
|  | Contractor's initial costs of providing sureties, insurance of the Works and plant, third party or public liability insurance and unemployment insurance to cover his compliance with the requirements of the Workmen's Compensation Act and any other initial financing obligations of a preliminary and general nature | sum | 1
A.1.1 |  | Office of 16 m² floor area | Sum | 1
A.1.2 |  | Storage shed of 20 m² floor area | Sum | 1
A.1.2 |  | Living accommodation for a project | Sum | 1
A.1.3 |  | Ablution facilities | Sum | 1
A.1.4 |  | Water supplies, electric power and communications | Sum | 1
A.1.6 |  | Occupational Health and Safety Requirements | Sum | 1
A.1.7 |  | Removal of site establishment for a project | Sum | 1
SUB-TOTAL SECTION "A.1" CARRIED FORWARD
A.2 | 8.3.1 | TIME RELATED ITEMS (5 % of SECTION B-E)
|  | Contractural requirements, general obligations and establishment, maintenance and removal of site facility. Provide security and take responsibility of material including adherence to all safety requirements. | sum | 1
A.2.1 |  | Office of 16 m² floor area | Sum | 1
A.2.2 |  | Storage shed of 20 m² floor area | Sum | 1
A.2.3 |  | Living accommodation for a project | Sum | 1
A.2.4 |  | Ablution facilities | Sum | 1
A.2.5 |  | Water supplies, electric power and communications | Sum | 1
A.2.6 |  | Occupational Health and Safety Requirements | Sum | 1
A.2.7 |  | Supervision for Duration of Construction | Months | 4
A.2.8 |  | Community liason officer | Months | 4
SUB-TOTAL SECTION "A.2" CARRIED FORWARD
| SANS 1200A | DAYWORKS
A.3 | 8.7 | Daywork Labour
A.3.1 |  | a) Contractor's Representative | hour | 1 |  | Rate Only
A.3.2 |  | b) Qualified Artisans | hour | 1 |  | Rate Only
A.3.3 |  | i) Plumber | hour | 1 |  | Rate Only
A.3.4 |  | ii) Boilermaker | hour | 1 |  | Rate Only
A.3.5 |  | iii) Bricklayer | hour | 1 |  | Rate Only
A.3.6 |  | iv) Plasterer | hour | 1 |  | Rate Only
A.3.7 |  | v) Welder with API 1104 Certificate | hour | 1 |  | Rate Only
A.3.8 |  | vi) Electrician | hour | 1 |  | Rate Only
A.3.10 |  | e) Semi-skilled labourer | hour | 1 |  | Rate Only
A.3.11 |  | f) Labourer | hour | 1 |  | Rate Only
A.4 | 8.7 | Plant hire : Work Rates on Site
A.4.1 |  | Crane 65 t - 80 t capacity | hour | 1 |  | Rate Only
A.4.2 |  | TLB 60 kW - 70 kW | hour | 1 |  | Rate Only
A.4.3 |  | Bulldozer 160 kW - 170 kW | hour | 1 |  | Rate Only
A.4.4 |  | Motor graders 150 kW - 160 kW | hour | 1 |  | Rate Only
A.4.5 |  | Wheel excavators 0,4 - 1,25m³ bucket size | hour | 1 |  | Rate Only
A.4.6 |  | Water tankers 4 000 - 20 000 litre | hour | 1 |  | Rate Only
A.4.8 |  | 6m³ Tip trucks | hour | 1 |  | Rate Only
A.4.9 |  | Plate compactors & tampers | hour | 1 |  | Rate Only
A.4.15 |  | Dumpers 0,5m³ (Hydraulic tip) | hour | 1 |  | Rate Only
A.4.16 |  | Mono pump with 80mm DN outlet (diesel driven) 2.2 - 7.5 kW | hour | 1 |  | Rate Only
A.4.17 |  | Arc-welding unit (300 A) | hour | 1 |  | Rate Only
A.4.19 |  | 10 kVA (petrol) 220V Generator | hour | 1 |  | Rate Only
A.4.20 |  | 30 kVA (diesel) 380V - 3ph Generator | hour | 1 |  | Rate Only
|  | TOTAL SECTION "A" CARRIED FORWARD TO SUMMARY |  |  | 0

## SUMMARY BELLEVUE
SUPPLY OF STOCKWATER AT BELLEVUE
SUMMARY OF SECTIONS
TOTAL SECTION B.2 : MAINLINE & RESEVOIRS
TOTAL SECTION B.3 : SOLAR SYSTEM
TOTAL SECTION B.4 : PUMP HOUSE
SUB TOTAL CARRIED TO SUMMARY

## B.2-Mainline & Resevoir
SECTION B: BELLEVUE FARM
No. | CLAUSE | SECTION B.2 : MAINLINE & RESEVOIR | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
B.2.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m (3m wide) | m2 | 9000
| SANS 1200D | EXCAVATION
B.2.2 |  | Excavations in all materials for trenches to a depth of 1100 mm and 600 mm wide (including bedding), backfill, compact and dispose of surplus material for PVC pipeline | m | 400
B.2.3 |  | Excavations in all materials for trenches to a depth of 700 mm and 400 mm wide (including bedding), backfill, compact and dispose of surplus material for HDPE pipeline | m | 2500
B.2.4 |  | Extra-over Item 2.3.1.4
B.2.5 |  | a) Intermediate excavations | mᶾ | 1
B.2.6 |  | b) Hard excavations | mᶾ | 1
B.2.7 |  | c) Boulder excavation, Class A | mᶾ | 1
B.2.8 |  | d) Boulder excavation, Class B | mᶾ | 1
PIPE AND FITTINGS
Supply, deliver ,install, lay and test the following: mPVC pipes (including all ancillary jointing materials and thrust blocks where applicable) to SABS 966 in 6m lengths with integral rubber ring joints
B.2.9 |  | 75 mm class 6 | m | 500
B.2.10 |  | Supply, lay, bed and test the following HDPE (SABS approved) pressure pipe complete with couplings (fittings)
B.2.11 |  | 40 mm class 6 | m | 3000
B.2.12 |  | 50 mm class 6 | m | 200
B.2.13 |  | 63 mm class 6 | m | 200
FITTINGS
B.2.14 |  | 50 mm Water Meter of the inferential type with interchangeable mechanism fitted with a magnetic coupling drive and straight-reading, registering in m3. Counter sealed to IP68 meter with built in capability of generating inductive pulse signals and pressure tapping as standard. Body flanges to be dual drilled to BS10 table D and BS 4504 Table 16 specifications. Meter body and cover to be epoxy powder coated | no | 1
B.2.15 |  | 50 mm in line strainer with heavy duty stainless sieve which is securely supported at the top and bottom of the strainer body. The sieve element must be removed from the top for cleaning purposes without disturbing the flange joints. The flanges to be dual drilled to allow connection to either BS11 Table D or BS4504 Table 16 flanges. | no | 1
B.2.16 |  | 50 mm galvanised nipple | no | 5
B.2.17 |  | 50 mm check valve | no | 2
B.2.18 |  | 50 x 32 mm galvanised tee | no | 2
B.2.19 |  | Pressure Gauge (0 - 600 KPa) - Glycerine filled | no | 2
B.2.20 |  | 50 mm x 1500 galvanised stand pipe , threaded both sides | no | 2
B.2.21 |  | Galv elbow 50 mm | no | 5
B.2.22 |  | Galv conical union 80 mm | no | 5
B.2.23 |  | Cast iron Base plate for borehole, split type 80mm | no | 1
B.2.24 |  | 50 mm x 32 mm saddle | no | 4
B.2.25 |  | 50 mm double purpose air valve | no | 6
B.2.26 |  | 32 mm x 1600 mm standpipe , threaded both sides | no | 6
B.2.27 |  | 32 mm galvanised elbow | no | 4
B.2.28 |  | 50 x 3000 mm galvanised pipe stand pipe , threaded both sides | no | 3
RESEVOIRS
B.2.29 |  | Supply deliver, install and fill a 50 000 litre steel panel resevoir complete with: *65 mm galvanised inlet pipe complete with bermard valve and strainer * 50 mm galvanised outlet pipe complete with gate valve *80 mm scour drain assembly *80 mm overflow pipe * Water Level indicator *Internal ladder complete with cage (galvanised stand) *External ladder complete with cage (galvanised stand) * 1000 gsm , UV stabilised , reinforced PVC liner *Galvanized, square tubular steel roof trusses covered with corrugated Zincalume® plated steel *hot-dip plated with highly corrosion resistant Zincalume® alloy for wall panels | no | 1
B.2.30 |  | Supply and lay 19 mm concrete stone around steel panel resevoirs | mᶾ | 1.4
B.2.31 |  | Supply and lay plaster sand under resevoirs | mᶾ | 6
CONCRETE WORKS
B.2.32 |  | Supply deliver and install a precast concrete 1000 l drinking trough complete with high pressure ball valve | no | 16
B.2.33 |  | Supply or cast concrete of minimum 15 Mpa for 7 m x 5 m x 100 mm apron around the drinking trough complete with stone pitching | m3 | 28
TOTAL SECTION "B.2" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## B-3-Solar System
SECTION B: BELLEVUE FARM
| CLAUSE | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
SECTION B.3 : SOLAR SYSTEM
SUBMERSIBLE PUMP SET & ACCESSORIES
B.3.1 |  | Supply and install a Multi-stage Submersible pump unit, 380 V, three phase motor, complete with lead out cable and flow inducer sleeve. *Pump duty (1 ℓ/s @ total head of 120 meter) (1) Make ………………………… (2) Model ……………………….. (3) Phase 380V (4) 2.2 kW …….. | no | 1
B.3.2 |  | 4-core submersible electric: cable : size 2.5 mm2 | m | 150
B.3.3 |  | 10mm nylon rope | no | 150
B.3.4 |  | Install 63 mm Class 12 HDPE SABS approved as down pipe | m | 120
SOLAR SYSTEM
B.3.4 |  | Supply deliver and install 300 w monocrystalline panels, 6 In series and two in parallel complte wih mounting brackects | no | 12
B.3.5 |  | 3 kW/ 48 V pure sine wave invertor complete with: *AC/DC compatibility *Overvoltage and undervoltage protection *Overload protection *Overcurrent protection *Overtemperature protection *No-load protection. *Operating history memory *Detachable control panel *Enclosure class IP66 *Automatic generator start *Display | no | 1
B.3.6 |  | Supply and install arrray to array cable for solar panels | sum | 1
B.3.7 |  | Supply and install DC Cicuit breakers and surge protector | sum | 1
B.3.8 |  | Supply and install Combined Junction Box for solar panels | sum | 1
GENERATOR
B.3.9 |  | 15 kVA diesel generator complete with: *Electric start *Automatic voltage regulator * Heavy duty wheels ( 360 mm, trailer type) *Automatic transfer switch | no | 1
TOTAL SECTION "B.3" CARRIED FORWARD TO SUMMARY

## B.4-Pump House
SECTION B: BELLEVUE FARM
| SANS 1200 A | SECTION B.4: PUMP HOUSE | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
B.4.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m | m2 | 40
B.4.2 | 8.2.1 | Demolish & remove all existing structures & equipment (including borehole equipment) | sum | 1
| SANS 1200D | EXCAVATION
B.4.3 |  | Excavate foundation, 690mm wide x 400mm deep | mᶾ | 5
B.4.4 |  | Extra-over Item 2.3.1.4
B.4.5 |  | a) Intermediate excavations | mᶾ | 1
B.4.6 |  | b) Hard excavations | mᶾ | 1
B.4.7 |  | c) Boulder excavation, Class A | mᶾ | 1
B.4.8 |  | d) Boulder excavation, Class B | mᶾ | 1
B.4.9 |  | Backfill & compact to 90% MOD AASHTO for resevoir ,pump station , shed structure | m2 | 25
CLOSURES
B.4.10 |  | b) Supply and install 915 x 2035 mm standard steel door and frame with a 4 lever lock (entrance door) | no | 1
B.4.11 |  | Supply , deliver and install 300 mm x 300 mm x 20 mm x 3 mm expanded mesh welded on 40mm x 3 mm angle iron for openings | no | 4
B.4.12 |  | b)145x70 precast lintel - 5400mm long | no | 28
B.4.13 |  | Corrosion protection to all structural steel (Galvanized) | no | 1
BRICKWORK AND BUILDING
B.4.14 |  | Supply and build 230mm wide wall with FBA bricks, point finish | m2 | 25
B.4.15 |  | Supply and install 375 micron Dampcourse 225mm under all external walls at the same level as the top of the concrete floor slab and 225 mm above ground level. | sum | 1
B.4.16 |  | Supply and include 220mm brick-force on every second course below lintels and on every course above lintels | sum | 1
B.4.17 |  | Supply and Apply smooth plaster to internal walls, 15mm - 20mm. Mix 1:3 | m2 | 47
CONCRETE WORKS
B.4.18 |  | Cast concrete of Strength concrete: 20MPa/19mm for the following
B.4.19 |  | a)Strip footing (690 X 230 mm) | m3 | 4
B.4.20 |  | b)Floor slab ( 100 mm thick) | m3 | 4
B.4.21 |  | c)Pump bases and roof slab complete with wood floated finish.Seal roof slab with approved sealant as specified by manufacturer | m3 | 1
B.4.22 |  | d) Generator base complete with steel floated finish | m3 | 1
TOTAL SECTION "D.4" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## Hanglip Summary
SUPPLY OF STOCKWATER AT HANGLIP
SUMMARY OF SECTIONS
TOTAL SECTION C.1 :MAINLINE & RESEVOIR
TOTAL SECTION C.2 : SOLAR SYSTEM
TOTAL SECTION C.3 : PUMP HOUSE
SUB TOTAL CARRIED TO SUMMARY

## C.1-Mainline & Resevoir
SECTION C: HANGLIP FARM
No. | CLAUSE | SECTION C.1 : MAINLINE & RESEVOIR | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
C.1.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m (3m wide) | m2 | 9000
| SANS 1200D | EXCAVATION
C.1.2 |  | Excavations in all materials for trenches to a depth of 1100 mm and 600 mm wide (including bedding), backfill, compact and dispose of surplus material for PVC pipeline | m | 400
C.1.3 |  | Excavations in all materials for trenches to a depth of 700 mm and 400 mm wide (including bedding), backfill, compact and dispose of surplus material for HDPE pipeline | m | 2500
C.1.4 |  | Extra-over Item 2.3.1.4
C.1.5 |  | a) Intermediate excavations | mᶾ | 1
C.1.6 |  | b) Hard excavations | mᶾ | 1
C.1.7 |  | c) Boulder excavation, Class A | mᶾ | 1
C.1.8 |  | d) Boulder excavation, Class B | mᶾ | 1
C.1.9 |  | PIPE AND FITTINGS
Supply, deliver ,install, lay and test the following: mPVC pipes (including all ancillary jointing materials and thrust blocks where applicable) to SABS 966 in 6m lengths with integral rubber ring joints
C.1.9 |  | 75 mm class 6 | m | 500
C.1.10 |  | Supply, lay, bed and test the following HDPE (SABS approved) pressure pipe complete with couplings (fittings)
C.1.11 |  | 40 mm class 6 | m | 3000
C.1.12 |  | 50 mm class 6 | m | 200
C.1.13 |  | 63 mm class 6 | m | 200
FITTINGS
C.1.14 |  | 50 mm Water Meter of the inferential type with interchangeable mechanism fitted with a magnetic coupling drive and straight-reading, registering in m3. Counter sealed to IP68 meter with built in capability of generating inductive pulse signals and pressure tapping as standard. Body flanges to be dual drilled to BS10 table D and BS 4504 Table 16 specifications. Meter body and cover to be epoxy powder coated | no | 1
C.1.15 |  | 50 mm in line strainer with heavy duty stainless sieve which is securely supported at the top and bottom of the strainer body. The sieve element must be removed from the top for cleaning purposes without disturbing the flange joints. The flanges to be dual drilled to allow connection to either BS11 Table D or BS4504 Table 16 flanges. | no | 1
C.1.16 |  | 50 mm galvanised nipple | no | 5
C.1.17 |  | 50 mm check valve | no | 2
C.1.18 |  | 50 x 32 mm galvanised tee | no | 2
C.1.19 |  | Pressure Gauge (0 - 600 KPa) - Glycerine filled | no | 2
C.1.20 |  | 50 mm x 1500 galvanised stand pipe , threaded both sides | no | 2
C.1.21 |  | Galv elbow 50 mm | no | 5
C.1.22 |  | Galv conical union 80 mm | no | 5
C.1.23 |  | Cast iron Base plate for borehole, split type 80mm | no | 1
C.1.24 |  | 50 mm x 32 mm saddle | no | 4
C.1.25 |  | 50 mm double purpose air valve | no | 6
C.1.26 |  | 32 mm x 1600 mm standpipe , threaded both sides | no | 6
C.1.27 |  | 32 mm galvanised elbow | no | 4
C.1.28 |  | 50 x 3000 mm galvanised pipe stand pipe , threaded both sides | no | 3
RESEVOIRS
C.1.29 |  | Supply deliver, install and fill a 50 000 litre steel panel resevoir complete with: *65 mm galvanised inlet pipe complete with bermard valve and strainer * 50 mm galvanised outlet pipe complete with gate valve *80 mm scour drain assembly *80 mm overflow pipe * Water Level indicator *Internal ladder complete with cage (galvanised stand) *External ladder complete with cage (galvanised stand) * 1000 gsm , UV stabilised , reinforced PVC liner *Galvanized, square tubular steel roof trusses covered with corrugated Zincalume® plated steel *hot-dip plated with highly corrosion resistant Zincalume® alloy for wall panels | no | 1
C.1.30 |  | Supply and lay 19 mm concrete stone around steel panel resevoirs | mᶾ | 1.4
C.1.31 |  | Supply and lay plaster sand under resevoirs | mᶾ | 6
CONCRETE WORKS
C.1.32 |  | Supply deliver and install a precast concrete 1000 l drinking trough complete with high pressure ball valve | no | 16
C.1.33 |  | Supply or cast concrete of minimum 15 Mpa for 7 m x 5 m x 100 mm apron around the drinking trough complete with stone pitching | m3 | 28
TOTAL SECTION "C.1" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## C.2-Solar system
SECTION B: BELLEVUE FARM
| CLAUSE | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
SECTION C.2 : SOLAR SYSTEM
SUBMERSIBLE PUMP SET & ACCESSORIES
C.2.1 |  | Supply and install a Multi-stage Submersible pump unit, 380 V, three phase motor, complete with lead out cable and flow inducer sleeve. *Pump duty (1 ℓ/s @ total head of 120 meter) (1) Make ………………………… (2) Model ……………………….. (3) Phase 380V (4) 2.2 kW …….. | no | 1
C.2.2 |  | 4-core submersible electric: cable : size 2.5 mm2 | m | 150
C.2.3 |  | 10mm nylon rope | no | 150
C.2.4 |  | Install 63 mm Class 12 HDPE SABS approved as down pipe | m | 120
SOLAR SYSTEM
C.2.5 |  | Supply deliver and install 300 w monocrystalline panels, 6 In series and two in parallel complte wih mounting brackects | no | 12
C.2.6 |  | 3 kW/ 48 V pure sine wave invertor complete with: *AC/DC compatibility *Overvoltage and undervoltage protection *Overload protection *Overcurrent protection *Overtemperature protection *No-load protection. *Operating history memory *Detachable control panel *Enclosure class IP66 *Automatic generator start *Display | no | 1
C.2.7 |  | Supply and install arrray to array cable for solar panels | sum | 1
C.2.8 |  | Supply and install DC Cicuit breakers and surge protector | sum | 1
C.2.9 |  | Supply and install Combined Junction Box for solar panels | sum | 1
GENERATOR
C.2.10 |  | 15 kVA diesel generator complete with: *Electric start *Automatic voltage regulator * Heavy duty wheels ( 360 mm, trailer type) *Automatic transfer switch | no | 1
TOTAL SECTION "C.2" CARRIED FORWARD TO SUMMARY

## C.3-Pump House
SECTION C: HANGLIP FARM
| SANS 1200 A | SECTION C.3: PUMP HOUSE | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
C.3.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m | m2 | 40
C.3.2 | 8.2.1 | Demolish & remove all existing structures & equipment (including borehole equipment) | sum | 1
| SANS 1200D | EXCAVATION
C.3.3 |  | Excavate foundation, 690mm wide x 400mm deep | mᶾ | 5
C.3.4 |  | Extra-over Item 2.3.1.4
C.3.5 |  | a) Intermediate excavations | mᶾ | 1
C.3.6 |  | b) Hard excavations | mᶾ | 1
C.3.7 |  | c) Boulder excavation, Class A | mᶾ | 1
C.3.8 |  | d) Boulder excavation, Class B | mᶾ | 1
C.3.9 |  | Backfill & compact to 90% MOD AASHTO for resevoir ,pump station , shed structure | m2 | 25
CLOSURES
C.3.10 |  | b) Supply and install 915 x 2035 mm standard steel door and frame with a 4 lever lock (entrance door) | no | 1
C.3.11 |  | Supply , deliver and install 300 mm x 300 mm x 20 mm x 3 mm expanded mesh welded on 40mm x 3 mm angle iron for openings | no | 4
C.3.12 |  | b)145x70 precast lintel - 5400mm long | no | 28
C.3.13 |  | Corrosion protection to all structural steel (Galvanized) | no | 1
BRICKWORK AND BUILDING
C.3.14 |  | Supply and build 230mm wide wall with FBA bricks, point finish | m2 | 25
C.3.15 |  | Supply and install 375 micron Dampcourse 225mm under all external walls at the same level as the top of the concrete floor slab and 225 mm above ground level. | sum | 1
C.3.16 |  | Supply and include 220mm brick-force on every second course below lintels and on every course above lintels | sum | 1
C.3.17 |  | Supply and Apply smooth plaster to internal walls, 15mm - 20mm. Mix 1:3 | m2 | 47
CONCRETE WORKS
C.3.18 |  | Cast concrete of Strength concrete: 20MPa/19mm for the following
C.3.19 |  | a)Strip footing (690 X 230 mm) | m3 | 4
C.3.20 |  | b)Floor slab ( 100 mm thick) | m3 | 4
C.3.21 |  | c)Pump bases and roof slab complete with wood floated finish.Seal roof slab with approved sealant as specified by manufacturer | m3 | 1
C.3.22 |  | d) Generator base complete with steel floated finish | m3 | 1
TOTAL SECTION "C.3" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## Doornport Summary
SUPPLY OF STOCKWATER AT DOORNPORT
SUMMARY OF SECTIONS
TOTAL SECTION D.2 :MAINLINE & RESEVOIR
TOTAL SECTION D.3 : SOLAR SYSTEM
TOTAL SECTION D.4 : PUMP HOUSE
SUB TOTAL CARRIED TO SUMMARY

## D.2-Mainline & Resevoir
SECTION D: DOORNPOORT FARM
No. | CLAUSE | SECTION D.2 : MAINLINE & RESEVOIR | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
D.2.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m (3m wide) | m2 | 9000
| SANS 1200D | EXCAVATION
D.2.2 |  | Excavations in all materials for trenches to a depth of 1100 mm and 600 mm wide (including bedding), backfill, compact and dispose of surplus material for PVC pipeline | m | 400
D.2.3 |  | Excavations in all materials for trenches to a depth of 700 mm and 400 mm wide (including bedding), backfill, compact and dispose of surplus material for HDPE pipeline | m | 2500
D.2.4 |  | Extra-over Item 2.3.1.4
D.2.5 |  | a) Intermediate excavations | mᶾ | 1
D.2.6 |  | b) Hard excavations | mᶾ | 1
D.2.7 |  | c) Boulder excavation, Class A | mᶾ | 1
D.2.8 |  | d) Boulder excavation, Class B | mᶾ | 1
PIPE AND FITTINGS
Supply, deliver ,install, lay and test the following: mPVC pipes (including all ancillary jointing materials and thrust blocks where applicable) to SABS 966 in 6m lengths with integral rubber ring joints
D.2.9 |  | 75 mm class 6 | m | 500
D.2.10 |  | Supply, lay, bed and test the following HDPE (SABS approved) pressure pipe complete with couplings (fittings)
D.2.11 |  | 40 mm class 6 | m | 3000
D.2.12 |  | 50 mm class 6 | m | 200
D.2.13 |  | 63 mm class 6 | m | 200
FITTINGS
D.2.14 |  | 50 mm Water Meter of the inferential type with interchangeable mechanism fitted with a magnetic coupling drive and straight-reading, registering in m3. Counter sealed to IP68 meter with built in capability of generating inductive pulse signals and pressure tapping as standard. Body flanges to be dual drilled to BS10 table D and BS 4504 Table 16 specifications. Meter body and cover to be epoxy powder coated | no | 1
D.2.15 |  | 50 mm in line strainer with heavy duty stainless sieve which is securely supported at the top and bottom of the strainer body. The sieve element must be removed from the top for cleaning purposes without disturbing the flange joints. The flanges to be dual drilled to allow connection to either BS11 Table D or BS4504 Table 16 flanges. | no | 1
D.2.16 |  | 50 mm galvanised nipple | no | 5
D.2.17 |  | 50 mm check valve | no | 2
D.2.18 |  | 50 x 32 mm galvanised tee | no | 2
D.2.19 |  | Pressure Gauge (0 - 600 KPa) - Glycerine filled | no | 2
D.2.20 |  | 50 mm x 1500 galvanised stand pipe , threaded both sides | no | 2
D.2.21 |  | Galv elbow 50 mm | no | 5
D.2.22 |  | Galv conical union 80 mm | no | 5
D.2.23 |  | Cast iron Base plate for borehole, split type 80mm | no | 1
D.2.24 |  | 50 mm x 32 mm saddle | no | 4
D.2.25 |  | 50 mm double purpose air valve | no | 6
D.2.26 |  | 32 mm x 1600 mm standpipe , threaded both sides | no | 6
D.2.27 |  | 32 mm galvanised elbow | no | 4
D.2.28 |  | 50 x 3000 mm galvanised pipe stand pipe , threaded both sides | no | 3
RESEVOIRS
D.2.29 |  | Supply deliver, install and fill a 50 000 litre steel panel resevoir complete with: *65 mm galvanised inlet pipe complete with bermard valve and strainer * 50 mm galvanised outlet pipe complete with gate valve *80 mm scour drain assembly *80 mm overflow pipe * Water Level indicator *Internal ladder complete with cage (galvanised stand) *External ladder complete with cage (galvanised stand) * 1000 gsm , UV stabilised , reinforced PVC liner *Galvanized, square tubular steel roof trusses covered with corrugated Zincalume® plated steel *hot-dip plated with highly corrosion resistant Zincalume® alloy for wall panels | no | 4
D.2.30 |  | Supply and lay 19 mm concrete stone around steel panel resevoirs | mᶾ | 1.4
D.2.31 |  | Supply and lay plaster sand under resevoirs | mᶾ | 6
CONCRETE WORKS
D.2.32 |  | Supply deliver and install a precast concrete 1000 l drinking trough complete with high pressure ball valve | no | 16
D.2.33 |  | Supply or cast concrete of minimum 15 Mpa for 7 m x 5 m x 100 mm apron around the drinking trough complete with stone pitching | m3 | 28
TOTAL SECTION "D.2" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## D-3-Solar System
SECTION D: DOORNPOORT FARM
| CLAUSE | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
SECTION D.3 : SOLAR SYSTEM
SUBMERSIBLE PUMP SET & ACCESSORIES
D.3.1 |  | Supply and install a Multi-stage Submersible pump unit, 380 V, three phase motor, complete with lead out cable and flow inducer sleeve. *Pump duty (1 ℓ/s @ total head of 120 meter) (1) Make ………………………… (2) Model ……………………….. (3) Phase 380V (4) 2.2 kW …….. | no | 1
D.3.2 |  | 4-core submersible electric: cable : size 2.5 mm2 | m | 150
D.3.3 |  | 10mm nylon rope | no | 150
D.3.4 |  | Install 63 mm Class 12 HDPE SABS approved as down pipe | m | 120
SOLAR SYSTEM
D.3.4 |  | Supply deliver and install 300 w monocrystalline panels, 6 In series and two in parallel complte wih mounting brackects | no | 12
D.3.5 |  | 3 kW/ 48 V pure sine wave invertor complete with: *AC/DC compatibility *Overvoltage and undervoltage protection *Overload protection *Overcurrent protection *Overtemperature protection *No-load protection. *Operating history memory *Detachable control panel *Enclosure class IP66 *Automatic generator start *Display | no | 1
D.3.6 |  | Supply and install arrray to array cable for solar panels | sum | 1
D.3.7 |  | Supply and install DC Cicuit breakers and surge protector | sum | 1
D.3.8 |  | Supply and install Combined Junction Box for solar panels | sum | 1
GENERATOR
D.3.9 |  | 15 kVA diesel generator complete with: *Electric start *Automatic voltage regulator * Heavy duty wheels ( 360 mm, trailer type) *Automatic transfer switch | no | 1
TOTAL SECTION "D.3" CARRIED FORWARD TO SUMMARY

## D.4-Pump House
SECTION D: DOORNPOORT FARM
| SANS 1200 A | SECTION B.4: PUMP HOUSE | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
D.4.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m | m2 | 40
D.4.2 | 8.2.1 | Demolish & remove all existing structures & equipment (including borehole equipment) | sum | 1
| SANS 1200D | EXCAVATION
D.4.3 |  | Excavate foundation, 690mm wide x 400mm deep | mᶾ | 5
D.4.4 |  | Extra-over Item 2.3.1.4
D.4.5 |  | a) Intermediate excavations | mᶾ | 1
D.4.6 |  | b) Hard excavations | mᶾ | 1
D.4.7 |  | c) Boulder excavation, Class A | mᶾ | 1
D.4.8 |  | d) Boulder excavation, Class B | mᶾ | 1
D.4.9 |  | Backfill & compact to 90% MOD AASHTO for resevoir ,pump station , shed structure | m2 | 25
CLOSURES
D.4.10 |  | b) Supply and install 915 x 2035 mm standard steel door and frame with a 4 lever lock (entrance door) | no | 1
D.4.11 |  | Supply , deliver and install 300 mm x 300 mm x 20 mm x 3 mm expanded mesh welded on 40mm x 3 mm angle iron for openings | no | 4
D.4.12 |  | b)145x70 precast lintel - 5400mm long | no | 28
D.4.13 |  | Corrosion protection to all structural steel (Galvanized) | no | 1
BRICKWORK AND BUILDING
D.4.14 |  | Supply and build 230mm wide wall with FBA bricks, point finish | m2 | 25
D.4.15 |  | Supply and install 375 micron Dampcourse 225mm under all external walls at the same level as the top of the concrete floor slab and 225 mm above ground level. | sum | 1
D.4.16 |  | Supply and include 220mm brick-force on every second course below lintels and on every course above lintels | sum | 1
D.4.17 |  | Supply and Apply smooth plaster to internal walls, 15mm - 20mm. Mix 1:3 | m2 | 47
CONCRETE WORKS
D.4.18 |  | Cast concrete of Strength concrete: 20MPa/19mm for the following
D.4.19 |  | a)Strip footing (690 X 230 mm) | m3 | 4
D.4.20 |  | b)Floor slab ( 100 mm thick) | m3 | 4
D.4.21 |  | c)Pump bases and roof slab complete with wood floated finish.Seal roof slab with approved sealant as specified by manufacturer | m3 | 1
D.4.22 |  | d) Generator base complete with steel floated finish | m3 | 1
TOTAL SECTION "D.4" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## SUMMARY VUURSTENLAGTE
SUPPLY OF STOCKWATER AT VUURSTENLAGTE
SUMMARY OF SECTIONS
TOTAL SECTION E.1 :MAINLINE & RESEVOIR
TOTAL SECTION E.2 : SOLAR SYSTEM
TOTAL SECTION E.3 : PUMP HOUSE
SUB TOTAL CARRIED TO SUMMARY

## E.1-Mainline & Resevoir (2)
SECTION E: VUURTENLAAGTE FARM
No. | CLAUSE | SECTION E.1 : MAINLINE & RESEVOIR | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
E.1.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m (3m wide) | m2 | 9000
| SANS 1200D | EXCAVATION
E.1.2 |  | Excavations in all materials for trenches to a depth of 1100 mm and 600 mm wide (including bedding), backfill, compact and dispose of surplus material for PVC pipeline | m | 400
E.1.3 |  | Excavations in all materials for trenches to a depth of 700 mm and 400 mm wide (including bedding), backfill, compact and dispose of surplus material for HDPE pipeline | m | 2500
E.1.4 |  | Extra-over Item 2.3.1.4
E.1.5 |  | a) Intermediate excavations | mᶾ | 1
E.1.6 |  | b) Hard excavations | mᶾ | 1
E.1.7 |  | c) Boulder excavation, Class A | mᶾ | 1
E.1.8 |  | d) Boulder excavation, Class B | mᶾ | 1
E.1.9 |  | PIPE AND FITTINGS
Supply, deliver ,install, lay and test the following: mPVC pipes (including all ancillary jointing materials and thrust blocks where applicable) to SABS 966 in 6m lengths with integral rubber ring joints
E.1.9 |  | 75 mm class 6 | m | 500
E.1.10 |  | Supply, lay, bed and test the following HDPE (SABS approved) pressure pipe complete with couplings (fittings)
E.1.11 |  | 40 mm class 6 | m | 3000
E.1.12 |  | 50 mm class 6 | m | 200
E.1.13 |  | 63 mm class 6 | m | 200
FITTINGS
E.1.14 |  | 50 mm Water Meter of the inferential type with interchangeable mechanism fitted with a magnetic coupling drive and straight-reading, registering in m3. Counter sealed to IP68 meter with built in capability of generating inductive pulse signals and pressure tapping as standard. Body flanges to be dual drilled to BS10 table D and BS 4504 Table 16 specifications. Meter body and cover to be epoxy powder coated | no | 1
E.1.15 |  | 50 mm in line strainer with heavy duty stainless sieve which is securely supported at the top and bottom of the strainer body. The sieve element must be removed from the top for cleaning purposes without disturbing the flange joints. The flanges to be dual drilled to allow connection to either BS11 Table D or BS4504 Table 16 flanges. | no | 1
E.1.16 |  | 50 mm galvanised nipple | no | 5
E.1.17 |  | 50 mm check valve | no | 2
E.1.18 |  | 50 x 32 mm galvanised tee | no | 2
E.1.19 |  | Pressure Gauge (0 - 600 KPa) - Glycerine filled | no | 2
E.1.20 |  | 50 mm x 1500 galvanised stand pipe , threaded both sides | no | 2
E.1.21 |  | Galv elbow 50 mm | no | 5
E.1.22 |  | Galv conical union 80 mm | no | 5
E.1.23 |  | Cast iron Base plate for borehole, split type 80mm | no | 1
E.1.24 |  | 50 mm x 32 mm saddle | no | 4
E.1.25 |  | 50 mm double purpose air valve | no | 6
E.1.26 |  | 32 mm x 1600 mm standpipe , threaded both sides | no | 6
E.1.27 |  | 32 mm galvanised elbow | no | 4
E.1.28 |  | 50 x 3000 mm galvanised pipe stand pipe , threaded both sides | no | 3
RESEVOIRS
E.1.29 |  | Supply deliver, install and fill a 50 000 litre steel panel resevoir complete with: *65 mm galvanised inlet pipe complete with bermard valve and strainer * 50 mm galvanised outlet pipe complete with gate valve *80 mm scour drain assembly *80 mm overflow pipe * Water Level indicator *Internal ladder complete with cage (galvanised stand) *External ladder complete with cage (galvanised stand) * 1000 gsm , UV stabilised , reinforced PVC liner *Galvanized, square tubular steel roof trusses covered with corrugated Zincalume® plated steel *hot-dip plated with highly corrosion resistant Zincalume® alloy for wall panels | no | 1
E.1.30 |  | Supply and lay 19 mm concrete stone around steel panel resevoirs | mᶾ | 1.4
E.1.31 |  | Supply and lay plaster sand under resevoirs | mᶾ | 6
CONCRETE WORKS
E.1.32 |  | Supply deliver and install a precast concrete 1000 l drinking trough complete with high pressure ball valve | no | 16
E.1.33 |  | Supply or cast concrete of minimum 15 Mpa for 7 m x 5 m x 100 mm apron around the drinking trough complete with stone pitching | m3 | 28
TOTAL SECTION "E.1" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## E.2-Solar system (2)
SECTION E: VUURTENLAAGTE FARM
| CLAUSE | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
SECTION E.2 : SOLAR SYSTEM
SUBMERSIBLE PUMP SET & ACCESSORIES
E.2.1 |  | Supply snd install a Multi-stage Submersible pump unit, 380 V, three phase motor, complete with lead out cable and flow inducer sleeve. *Pump duty (1 ℓ/s @ total head of 120 meter) (1) Make ………………………… (2) Model ……………………….. (3) Phase 380V (4) 2.2 kW …….. | no | 1
E.2.2 |  | 4-core submersible electric: cable : size 2.5 mm2 | m | 150
E.2.3 |  | 10mm nylon rope | no | 150
E.2.4 |  | Install 63 mm Class 12 HDPE SABS approved as down pipe | m | 120
SUB-TOTAL SECTION "B.1" CARRIED FORWARD
SOLAR SYSTEM
E.2.5 |  | Supply deliver and install 300 w monocrystalline panels, 6 In series and two in parallel complte wih mounting brackects | no | 12
E.2.6 |  | 3 kW/ 48 V pure sine wave invertor complete with: *AC/DC compatibility *Overvoltage and undervoltage protection *Overload protection *Overcurrent protection *Overtemperature protection *No-load protection. *Operating history memory *Detachable control panel *Enclosure class IP66 *Automatic generator start *Display | no | 1
E.2.7 |  | Supply and install arrray to array cable for solar panels | sum | 1
E.2.8 |  | Supply and install DC Cicuit breakers and surge protector | sum | 1
E.2.9 |  | Supply and install Combined Junction Box for solar panels | sum | 1
GENERATOR
E.2.10 |  | 15 kVA diesel generator complete with: *Electric start *Automatic voltage regulator * Heavy duty wheels ( 360 mm, trailer type) *Automatic transfer switch | no | 1
TOTAL SECTION "B.3" CARRIED FORWARD TO SUMMARY

## E.3-Pump House
SECTION E: VUURTENLAAGTE FARM
| SANS 1200 A | SECTION E.3: PUMP HOUSE | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
E.3.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m | m2 | 40
E.3.2 | 8.2.1 | Demolish & remove all existing structures & equipment (including borehole equipment) | sum | 1
| SANS 1200D | EXCAVATION
E.3.3 |  | Excavate foundation, 690mm wide x 400mm deep | mᶾ | 5
E.3.4 |  | Extra-over Item 2.3.1.4
E.3.5 |  | a) Intermediate excavations | mᶾ | 1
E.3.6 |  | b) Hard excavations | mᶾ | 1
E.3.7 |  | c) Boulder excavation, Class A | mᶾ | 1
E.3.8 |  | d) Boulder excavation, Class B | mᶾ | 1
E.3.9 |  | Backfill & compact to 90% MOD AASHTO for resevoir ,pump station , shed structure | m2 | 25
CLOSURES
E.3.10 |  | b) Supply and install 915 x 2035 mm standard steel door and frame with a 4 lever lock (entrance door) | no | 1
E.3.11 |  | Supply , deliver and install 300 mm x 300 mm x 20 mm x 3 mm expanded mesh welded on 40mm x 3 mm angle iron for openings | no | 4
E.3.12 |  | b)145x70 precast lintel - 5400mm long | no | 28
E.3.13 |  | Corrosion protection to all structural steel (Galvanized) | no | 1
BRICKWORK AND BUILDING
E.3.14 |  | Supply and build 230mm wide wall with FBA bricks, point finish | m2 | 25
E.3.15 |  | Supply and install 375 micron Dampcourse 225mm under all external walls at the same level as the top of the concrete floor slab and 225 mm above ground level. | sum | 1
E.3.16 |  | Supply and include 220mm brick-force on every second course below lintels and on every course above lintels | sum | 1
E.3.17 |  | Supply and Apply smooth plaster to internal walls, 15mm - 20mm. Mix 1:3 | m2 | 47
CONCRETE WORKS
E.3.18 |  | Cast concrete of Strength concrete: 20MPa/19mm for the following
E.3.19 |  | a)Strip footing (690 X 230 mm) | m3 | 4
E.3.20 |  | b)Floor slab ( 100 mm thick) | m3 | 4
E.3.21 |  | c)Pump bases and roof slab complete with wood floated finish.Seal roof slab with approved sealant as specified by manufacturer | m3 | 1
E.3.22 |  | d) Generator base complete with steel floated finish | m3 | 1
TOTAL SECTION "E.3" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## VANHEINING Summary
SUPPLY OF STOCKWATER AT VANHEINING
SUMMARY OF SECTIONS
TOTAL SECTION F.1 :MAINLINE & RESEVOIR
TOTAL SECTION F.2 : SOLAR SYSTEM
TOTAL SECTION F.3 : PUMP HOUSE
SUB TOTAL CARRIED TO SUMMARY

## F.2-Mainline & Resevoir
SECTION F: VANHEINING FARM
No. | CLAUSE | SECTION F.2 : MAINLINE & RESEVOIR | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
F.2.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m (3m wide) | m2 | 9000
| SANS 1200D | EXCAVATION
F.2.2 |  | Excavations in all materials for trenches to a depth of 1100 mm and 600 mm wide (including bedding), backfill, compact and dispose of surplus material for PVC pipeline | m | 400
F.2.3 |  | Excavations in all materials for trenches to a depth of 700 mm and 400 mm wide (including bedding), backfill, compact and dispose of surplus material for HDPE pipeline | m | 2500
F.2.4 |  | Extra-over Item 2.3.1.4
F.2.5 |  | a) Intermediate excavations | mᶾ | 1
F.2.6 |  | b) Hard excavations | mᶾ | 1
F.2.7 |  | c) Boulder excavation, Class A | mᶾ | 1
F.2.8 |  | d) Boulder excavation, Class B | mᶾ | 1
PIPE AND FITTINGS
Supply, deliver ,install, lay and test the following: mPVC pipes (including all ancillary jointing materials and thrust blocks where applicable) to SABS 966 in 6m lengths with integral rubber ring joints
F.2.9 |  | 75 mm class 6 | m | 500
F.2.10 |  | Supply, lay, bed and test the following HDPE (SABS approved) pressure pipe complete with couplings (fittings)
F.2.11 |  | 40 mm class 6 | m | 3000
F.2.12 |  | 50 mm class 6 | m | 200
F.2.13 |  | 63 mm class 6 | m | 200
FITTINGS
F.2.14 |  | 50 mm Water Meter of the inferential type with interchangeable mechanism fitted with a magnetic coupling drive and straight-reading, registering in m3. Counter sealed to IP68 meter with built in capability of generating inductive pulse signals and pressure tapping as standard. Body flanges to be dual drilled to BS10 table D and BS 4504 Table 16 specifications. Meter body and cover to be epoxy powder coated | no | 1
F.2.15 |  | 50 mm in line strainer with heavy duty stainless sieve which is securely supported at the top and bottom of the strainer body. The sieve element must be removed from the top for cleaning purposes without disturbing the flange joints. The flanges to be dual drilled to allow connection to either BS11 Table D or BS4504 Table 16 flanges. | no | 1
F.2.16 |  | 50 mm galvanised nipple | no | 5
F.2.17 |  | 50 mm check valve | no | 2
F.2.18 |  | 50 x 32 mm galvanised tee | no | 2
F.2.19 |  | Pressure Gauge (0 - 600 KPa) - Glycerine filled | no | 2
F.2.20 |  | 50 mm x 1500 galvanised stand pipe , threaded both sides | no | 2
F.2.21 |  | Galv elbow 50 mm | no | 5
F.2.22 |  | Galv conical union 80 mm | no | 5
F.2.23 |  | Cast iron Base plate for borehole, split type 80mm | no | 1
F.2.24 |  | 50 mm x 32 mm saddle | no | 4
F.2.25 |  | 50 mm double purpose air valve | no | 6
F.2.26 |  | 32 mm x 1600 mm standpipe , threaded both sides | no | 6
F.2.27 |  | 32 mm galvanised elbow | no | 4
F.2.28 |  | 50 x 3000 mm galvanised pipe stand pipe , threaded both sides | no | 3
RESEVOIRS
F.2.29 |  | Supply deliver, install and fill a 50 000 litre steel panel resevoir complete with: *65 mm galvanised inlet pipe complete with bermard valve and strainer * 50 mm galvanised outlet pipe complete with gate valve *80 mm scour drain assembly *80 mm overflow pipe * Water Level indicator *Internal ladder complete with cage (galvanised stand) *External ladder complete with cage (galvanised stand) * 1000 gsm , UV stabilised , reinforced PVC liner *Galvanized, square tubular steel roof trusses covered with corrugated Zincalume® plated steel *hot-dip plated with highly corrosion resistant Zincalume® alloy for wall panels | no | 4
F.2.30 |  | Supply and lay 19 mm concrete stone around steel panel resevoirs | mᶾ | 1.4
F.2.31 |  | Supply and lay plaster sand under resevoirs | mᶾ | 6
CONCRETE WORKS
F.2.32 |  | Supply deliver and install a precast concrete 1000 l drinking trough complete with high pressure ball valve | no | 16
F.2.33 |  | Supply or cast concrete of minimum 15 Mpa for 7 m x 5 m x 100 mm apron around the drinking trough complete with stone pitching | m3 | 28
TOTAL SECTION "F.2" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## F-3-Solar System
SECTION F: VANHEINING FARM
| CLAUSE | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
SECTION F.3 : SOLAR SYSTEM
SUBMERSIBLE PUMP SET & ACCESSORIES
F.3.1 |  | Supply and install a Multi-stage Submersible pump unit, 380 V, three phase motor, complete with lead out cable and flow inducer sleeve. *Pump duty (1 ℓ/s @ total head of 120 meter) (1) Make ………………………… (2) Model ……………………….. (3) Phase 380V (4) 2.2 kW …….. | no | 1
F.3.2 |  | 4-core submersible electric: cable : size 2.5 mm2 | m | 150
F.3.3 |  | 10mm nylon rope | no | 150
F.3.4 |  | Install 63 mm Class 12 HDPE SABS approved as down pipe | m | 120
SUB-TOTAL SECTION "B.1" CARRIED FORWARD
SOLAR SYSTEM
F.3.4 |  | Supply deliver and install 300 w monocrystalline panels, 6 In series and two in parallel complte wih mounting brackects | no | 12
F.3.5 |  | 3 kW/ 48 V pure sine wave invertor complete with: *AC/DC compatibility *Overvoltage and undervoltage protection *Overload protection *Overcurrent protection *Overtemperature protection *No-load protection. *Operating history memory *Detachable control panel *Enclosure class IP66 *Automatic generator start *Display | no | 1
F.3.6 |  | Supply and install arrray to array cable for solar panels | sum | 1
F.3.7 |  | Supply and install DC Cicuit breakers and surge protector | sum | 1
F.3.8 |  | Supply and install Combined Junction Box for solar panels | sum | 1
GENERATOR
F.3.9 |  | 15 kVA diesel generator complete with: *Electric start *Automatic voltage regulator * Heavy duty wheels ( 360 mm, trailer type) *Automatic transfer switch | no | 1
TOTAL SECTION "F.3" CARRIED FORWARD TO SUMMARY

## F.4-Pump House
SECTION F: VANHEINING FARM
| SANS 1200 A | SECTION F.4: PUMP HOUSE | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
F.4.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m | m2 | 40
F.4.2 | 8.2.1 | Demolish & remove all existing structures & equipment (including borehole equipment) | sum | 1
| SANS 1200D | EXCAVATION
F.4.3 |  | Excavate foundation, 690mm wide x 400mm deep | mᶾ | 5
F.4.4 |  | Extra-over Item 2.3.1.4
F.4.5 |  | a) Intermediate excavations | mᶾ | 1
F.4.6 |  | b) Hard excavations | mᶾ | 1
F.4.7 |  | c) Boulder excavation, Class A | mᶾ | 1
F.4.8 |  | d) Boulder excavation, Class B | mᶾ | 1
F.4.9 |  | Backfill & compact to 90% MOD AASHTO for resevoir ,pump station , shed structure | m2 | 25
CLOSURES
F.4.10 |  | b) Supply and install 915 x 2035 mm standard steel door and frame with a 4 lever lock (entrance door) | no | 1
F.4.11 |  | Supply , deliver and install 300 mm x 300 mm x 20 mm x 3 mm expanded mesh welded on 40mm x 3 mm angle iron for openings | no | 4
F.4.12 |  | b)145x70 precast lintel - 5400mm long | no | 28
F.4.13 |  | Corrosion protection to all structural steel (Galvanized) | no | 1
BRICKWORK AND BUILDING
F.4.14 |  | Supply and build 230mm wide wall with FBA bricks, point finish | m2 | 25
F.4.15 |  | Supply and install 375 micron Dampcourse 225mm under all external walls at the same level as the top of the concrete floor slab and 225 mm above ground level. | sum | 1
F.4.16 |  | Supply and include 220mm brick-force on every second course below lintels and on every course above lintels | sum | 1
F.4.17 |  | Supply and Apply smooth plaster to internal walls, 15mm - 20mm. Mix 1:3 | m2 | 47
CONCRETE WORKS
F.4.18 |  | Cast concrete of Strength concrete: 20MPa/19mm for the following
F.4.19 |  | a)Strip footing (690 X 230 mm) | m3 | 4
F.4.20 |  | b)Floor slab ( 100 mm thick) | m3 | 4
F.4.21 |  | c)Pump bases and roof slab complete with wood floated finish.Seal roof slab with approved sealant as specified by manufacturer | m3 | 1
F.4.22 |  | d) Generator base complete with steel floated finish | m3 | 1
TOTAL SECTION "F.4" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## APPELFONTEIN Summary (2)
SUPPLY OF STOCKWATER AT APPELFONTEIN
SUMMARY OF SECTIONS
TOTAL SECTION G.2 :MAINLINE & RESEVOIR
TOTAL SECTION G.3 : SOLAR SYSTEM
TOTAL SECTION G.4 : PUMP HOUSE
SUB TOTAL CARRIED TO SUMMARY

## G.2-Mainline & Resevoir (2)
SECTION G: APPELFONTEIN FARM
No. | CLAUSE | SECTION G.2 : MAINLINE & RESEVOIR | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
G.2.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m (3m wide) | m2 | 9000
| SANS 1200D | EXCAVATION
G.2.2 |  | Excavations in all materials for trenches to a depth of 1100 mm and 600 mm wide (including bedding), backfill, compact and dispose of surplus material for PVC pipeline | m | 400
G.2.3 |  | Excavations in all materials for trenches to a depth of 700 mm and 400 mm wide (including bedding), backfill, compact and dispose of surplus material for HDPE pipeline | m | 2500
G.2.4 |  | Extra-over Item 2.3.1.4
G.2.5 |  | a) Intermediate excavations | mᶾ | 1
G.2.6 |  | b) Hard excavations | mᶾ | 1
G.2.7 |  | c) Boulder excavation, Class A | mᶾ | 1
G.2.8 |  | d) Boulder excavation, Class B | mᶾ | 1
PIPE AND FITTINGS
Supply, deliver ,install, lay and test the following: mPVC pipes (including all ancillary jointing materials and thrust blocks where applicable) to SABS 966 in 6m lengths with integral rubber ring joints
G.2.9 |  | 75 mm class 6 | m | 500
G.2.10 |  | Supply, lay, bed and test the following HDPE (SABS approved) pressure pipe complete with couplings (fittings)
G.2.11 |  | 40 mm class 6 | m | 3000
G.2.12 |  | 50 mm class 6 | m | 200
G.2.13 |  | 63 mm class 6 | m | 200
FITTINGS
G.2.14 |  | 50 mm Water Meter of the inferential type with interchangeable mechanism fitted with a magnetic coupling drive and straight-reading, registering in m3. Counter sealed to IP68 meter with built in capability of generating inductive pulse signals and pressure tapping as standard. Body flanges to be dual drilled to BS10 table D and BS 4504 Table 16 specifications. Meter body and cover to be epoxy powder coated | no | 1
G.2.15 |  | 50 mm in line strainer with heavy duty stainless sieve which is securely supported at the top and bottom of the strainer body. The sieve element must be removed from the top for cleaning purposes without disturbing the flange joints. The flanges to be dual drilled to allow connection to either BS11 Table D or BS4504 Table 16 flanges. | no | 1
G.2.16 |  | 50 mm galvanised nipple | no | 5
G.2.17 |  | 50 mm check valve | no | 2
G.2.18 |  | 50 x 32 mm galvanised tee | no | 2
G.2.19 |  | Pressure Gauge (0 - 600 KPa) - Glycerine filled | no | 2
G.2.20 |  | 50 mm x 1500 galvanised stand pipe , threaded both sides | no | 2
G.2.21 |  | Galv elbow 50 mm | no | 5
G.2.22 |  | Galv conical union 50 mm | no | 5
G.2.23 |  | Cast iron Base plate for borehole, split type 80mm | no | 1
G.2.24 |  | 50 mm x 32 mm saddle | no | 4
G.2.25 |  | 50 mm double purpose air valve | no | 6
G.2.26 |  | 32 mm x 1600 mm standpipe , threaded both sides | no | 6
G.2.27 |  | 32 mm galvanised elbow | no | 4
G.2.28 |  | 50 x 3000 mm galvanised pipe stand pipe , threaded both sides | no | 3
RESEVOIRS
G.2.29 |  | Supply deliver, install and fill a 50 000 litre steel panel resevoir complete with: *65 mm galvanised inlet pipe complete with bermard valve and strainer * 50 mm galvanised outlet pipe complete with gate valve *80 mm scour drain assembly *80 mm overflow pipe * Water Level indicator *Internal ladder complete with cage (galvanised stand) *External ladder complete with cage (galvanised stand) * 1000 gsm , UV stabilised , reinforced PVC liner *Galvanized, square tubular steel roof trusses covered with corrugated Zincalume® plated steel *hot-dip plated with highly corrosion resistant Zincalume® alloy for wall panels | no | 4
G.2.30 |  | Supply and lay 19 mm concrete stone around steel panel resevoirs | mᶾ | 1.4
G.2.31 |  | Supply and lay plaster sand under resevoirs | mᶾ | 6
CONCRETE WORKS
G.2.32 |  | Supply deliver and install a precast concrete 1000 l drinking trough complete with high pressure ball valve | no | 16
G.2.33 |  | Supply or cast concrete of minimum 15 Mpa for 7 m x 5 m x 100 mm apron around the drinking trough complete with stone pitching | m3 | 28
TOTAL SECTION "G.2" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+

## G-3-Solar System (2)
SECTION G: APPELFONTEIN FARM
| CLAUSE | DESCRIPTION | UNIT | QTY | RATE | AMOUNT
SECTION G.3 : SOLAR SYSTEM
SUBMERSIBLE PUMP SET & ACCESSORIES
G.3.1 |  | Supply snd install a Multi-stage Submersible pump unit, 380 V, three phase motor, complete with lead out cable and flow inducer sleeve. *Pump duty (1 ℓ/s @ total head of 120 meter) (1) Make ………………………… (2) Model ……………………….. (3) Phase 380V (4) 2.2 kW …….. | no | 1
G.3.2 |  | 4-core submersible electric: cable : size 2.5 mm2 | m | 150
G.3.3 |  | 10mm nylon rope | no | 150
G.3.4 |  | Install 63 mm Class 12 HDPE SABS approved as down pipe | m | 120
SUB-TOTAL SECTION "B.1" CARRIED FORWARD
SOLAR SYSTEM
G.3.4 |  | Supply deliver and install 300 w monocrystalline panels, 6 In series and two in parallel complte wih mounting brackects | no | 12
G.3.5 |  | 3 kW/ 48 V pure sine wave invertor complete with: *AC/DC compatibility *Overvoltage and undervoltage protection *Overload protection *Overcurrent protection *Overtemperature protection *No-load protection. *Operating history memory *Detachable control panel *Enclosure class IP66 *Automatic generator start *Display | no | 1
G.3.6 |  | Supply and install arrray to array cable for solar panels | sum | 1
G.3.7 |  | Supply and install DC Cicuit breakers and surge protector | sum | 1
G.3.8 |  | Supply and install Combined Junction Box for solar panels | sum | 1
GENERATOR
G.3.9 |  | 15 kVA diesel generator complete with: *Electric start *Automatic voltage regulator * Heavy duty wheels ( 360 mm, trailer type) *Automatic transfer switch | no | 1
TOTAL SECTION "F.3" CARRIED FORWARD TO SUMMARY

## G.4-Pump House (2)
SECTION G: APPELFONTEIN FARM
| SANS 1200 A | SECTION G.4: PUMP HOUSE | UNIT | QTY | RATE | AMOUNT
| SANS 1200C | SITE CLEARANCE
G.4.1 | 8.2.1 | Clear and grub site including vegetation, trees and tree stumps of girth up to 1m | m2 | 40
G.4.2 | 8.2.1 | Demolish & remove all existing structures & equipment (including borehole equipment) | sum | 1
| SANS 1200D | EXCAVATION
G.4.3 |  | Excavate foundation, 690mm wide x 400mm deep | mᶾ | 5
G.4.4 |  | Extra-over Item 2.3.1.4
G.4.5 |  | a) Intermediate excavations | mᶾ | 1
G.4.6 |  | b) Hard excavations | mᶾ | 1
G.4.7 |  | c) Boulder excavation, Class A | mᶾ | 1
G.4.8 |  | d) Boulder excavation, Class B | mᶾ | 1
G.4.9 |  | Backfill & compact to 90% MOD AASHTO for resevoir ,pump station , shed structure | m2 | 25
CLOSURES
G.4.10 |  | b) Supply and install 915 x 2035 mm standard steel door and frame with a 4 lever lock (entrance door) | no | 1
G.4.11 |  | Supply , deliver and install 300 mm x 300 mm x 20 mm x 3 mm expanded mesh welded on 40mm x 3 mm angle iron for openings | no | 4
G.4.12 |  | b)145x70 precast lintel - 5400mm long | no | 28
G.4.13 |  | Corrosion protection to all structural steel (Galvanized) | no | 1
BRICKWORK AND BUILDING
G.4.14 |  | Supply and build 230mm wide wall with FBA bricks, point finish | m2 | 25
G.4.15 |  | Supply and install 375 micron Dampcourse 225mm under all external walls at the same level as the top of the concrete floor slab and 225 mm above ground level. | sum | 1
G.4.16 |  | Supply and include 220mm brick-force on every second course below lintels and on every course above lintels | sum | 1
G.4.17 |  | Supply and Apply smooth plaster to internal walls, 15mm - 20mm. Mix 1:3 | m2 | 47
CONCRETE WORKS
G.4.18 |  | Cast concrete of Strength concrete: 20MPa/19mm for the following
G.4.19 |  | a)Strip footing (690 X 230 mm) | m3 | 4
G.4.20 |  | b)Floor slab ( 100 mm thick) | m3 | 4
G.4.21 |  | c)Pump bases and roof slab complete with wood floated finish.Seal roof slab with approved sealant as specified by manufacturer | m3 | 1
G.4.22 |  | d) Generator base complete with steel floated finish | m3 | 1
TOTAL SECTION "G.4" CARRIED FORWARD TO SUMMARY
Note on E5: Mailula Joseph Matome: Clearing for shed (240)+ 50 k resevoirs (72*4) + pipeline (4*5200) + big resevoir (154)+ pipeline hdpe (3*2500)+